## Gantt Chat
Semester One
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13
Tasks | Week 1: 1/10/2019; Week 7: 2/18/2019; Week 13: 4/1/2019
Form a team | bar: Week 1
Select a project | bar: Week 2 to Week 4
Requirement Analysis | bar: Week 3 to Week 4
Block Diagram desgin | bar: Week 4 to Week 6
Design Documents | bar: Week 4 to Week 6
Preliminary Design Review (PDR) | Week 7: PDR
Hardware Design | bar: Week 7 to Week 11
Software Design | bar: Week 9 to Week 12
Web Design | bar: Week 10 to Week 12
Midway Report | bar: Week 11 to Week 12
Midway Design Review (MDR) | Week 13: MDR
Semester Two
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13
Tasks
Software Design
Testig & Enhancement
Comprehensive Design Review (CDR) | Week 6: CDR
Final Report | bar: Week 11 to Week 12
Final Project Review (FPR) | Week 13: FPR
Public Presentations | bar: Week 13

## Tasks
System bring up | 2 months
LED control | 2 weeks
LCD driver | 2 weeks
USB wifi driver | 1 month
WPS | 2 weeks
wifi connect with phone for first configuration | 2 weeks
wifi connect with router | 1 week
lock configure web | 3 weeks
APP in phone | 1 month
APP connect with lock by cloud techology | 1 week
basic features in APP | 2 weeks
show lock status in LED | 1 week
show lock or face to LCD | two months